## Timeline Chart- OBT
Running Time for OBT- NT using IRV
Year | 2024 |  |  | 2025 |  |  |  | 2026
Particulars | Q2 (Feb-Mar) | Q3 (Apr-Jun) | Q4 (Jul-Sep) | Q1 (Oct-Dec) | Q2 (Jan-Mar) | Q3 (Apr-Jun) | Q4 (Jul-Sep) | Q1 (Oct-Dec) | Q2 (Jan-Mar) | Q3 (Apr-Jun) | Q4 (Jul-Sep)
Set-Up & Initial Training workshop | SETUP & TRAINING
Stage - 1 Proofreading |  | Luke, 1 Corinthians | Acts, 1 Timothy, 2 Timothy, Titus | 1 Thessalonians, 2 Thessalonians, Ephesians, Colossians, Philippians, 1 Peter | Matthew, 2 Peter, James, 1 John, 2 John, 3 John, Jude | Romans, John, Galatians, 2 Corinthians | Mark, Philemon | Hebrews, Revelation
Stage - 2 Community Checking |  |  | Luke, 1 Corinthians | Acts, 1 Timothy, 2 Timothy, Titus | 1 Thessalonians, 2 Thessalonians, Ephesians, Colossians, Philippians, 1 Peter | Matthew, 2 Peter, James, 1 John, 2 John, 3 John, Jude | Romans, John, Galatians, 2 Corinthians | Mark, Philemon | Hebrews,Revelation
Stage - 3 Linguist Checking |  |  |  | Luke, 1 Corinthians | Acts, 1 Timothy, 2 Timothy, Titus | 1 Thessalonians, 2 Thessalonians, Ephesians, Colossians, Philippians, 1 Peter | Matthew, 2 Peter, James, 1 John, 2 John, 3 John, Jude | Romans, John, Galatians, 2 Corinthians | Mark, Philemon | Hebrews,Revelation
Formatting, Editing and Publishing |  |  |  |  | Luke, 1 Corinthians | Acts, 1 Timothy, 2 Timothy, Titus | 1 Thessalonians, 2 Thessalonians, Ephesians, Colossians, Philippians, 1 Peter | Matthew, 2 Peter, James, 1 John, 2 John, 3 John, Jude | Romans, John, Galatians, 2 Corinthians | Mark, Philemon | Hebrews,Revelation & Release Event

## Sheet1 (hidden)
Oct-Dec | Q1
Jan-Mar | Q2
April-June | Q3
July-Sep | Q4
Training, Stage 1 Recording | BCS and ISL Community
Training, Stage 2 Community Check | ISL Community
Training, Stage 3 Sign Expert Check | ISLTRC Trained Panel
Training, Stage 4 Church Leader Check | Deaf Churches
Final Recording | BCS
Training, Stage 1 Recording

## Timeline Chart (Written NT)
Running Time for BT- NT using IRV
Year | 2024 |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027
Particulars | Q2 (Feb-March) | Q3 (Apr-Jun) | Q4 (Jul-Sep) | Q1 (Oct-Dec) | Q2 (Jan-March) | Q3 (Apr-Jun) | Q4 (Jul-Sep) | Q1 (Oct-Dec) | Q2 (Jan-March) | Q3 (Apr-Jun) | Q4 (Jul-Sep) | Q1 (Oct-Dec) | Q2 (Jan)
Set-Up & Initial Training workshop | SETUP & TRAINING
Stage - 1 Proofreading |  | Mark | Luke | Acts | Romans, 1 Corinthians | Galatians, Ephesians, Colosians, Philipians, 2 Peter, 1 John, 2 John, 3 John, Jude, Revelation | John, 2 Corinthians, 1 Thessalonians, 2 Thessalonians, 1 Timothy, 2 Timothy, Hebrews, James | Matthew, Titus, Philemon, 1 Peter
Stage - 2 Community Checking |  |  | Mark | Luke | Acts | Romans, 1 Corinthians | Galatians, Ephesians, Colosians, Philipians, 2 Peter, 1 John, 2 John, 3 John, Jude, Revelation | John, 2 Corinthians, 1 Thessalonians, 2 Thessalonians, 1 Timothy, 2 Timothy, Hebrews, James | Matthew, Titus, Philemon, 1 Peter
Stage - 3 Linguist Checking |  |  |  | Mark | Luke | Acts | Romans, 1 Corinthians | Galatians, Ephesians, Colosians, Philipians, 2 Peter, 1 John, 2 John, 3 John, Jude, Revelation | John, 2 Corinthians, 1 Thessalonians, 2 Thessalonians, 1 Timothy, 2 Timothy, Hebrews, James | Matthew, Titus, Philemon, 1 Peter
Stage - 4 Theological Checking |  |  |  |  | Mark | Luke | Acts | Romans, 1 Corinthians | Galatians, Ephesians, Colosians, Philipians, 2 Peter, 1 John, 2 John, 3 John, Jude, Revelation | John, 2 Corinthians, 1 Thessalonians, 2 Thessalonians, 1 Timothy, 2 Timothy, Hebrews, James | Matthew, Titus, Philemon, 1 Peter
Stage - 5 Consultant Checking | [5 empty] | Mark | Luke | Acts | Romans, 1 Corinthians | Galatians, Ephesians, Colosians, Philipians, 2 Peter, 1 John, 2 John, 3 John, Jude, Revelation | John, 2 Corinthians, 1 Thessalonians, 2 Thessalonians, 1 Timothy, 2 Timothy, Hebrews, James | Matthew, Titus, Philemon, 1 Peter
Formatting, Editing and Publishing | [6 empty] | Mark | Luke | Acts | Romans, 1 Corinthians | Galatians, Ephesians, Colosians, Philipians, 2 Peter, 1 John, 2 John, 3 John, Jude, Revelation | John, 2 Corinthians, 1 Thessalonians, 2 Thessalonians, 1 Timothy, 2 Timothy, Hebrews, James | Matthew, Titus, Philemon, 1 Peter